## Gant chart
Project plan |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
|  | Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Research
Kickoff with Lofthus - Presentation of Lofthus | Lofthus | Milestone | M
Research About Lofthus | Project manager | 50 |  | 4 | 4
Gather needs for website | Project manager | 50 |  | 4 | 4 | 4
Write functional spesification | Project manager | 50 |  |  |  | 4 | 4
Customer presentation meeting | Project manager | Milestone | [5 empty] | M
Design presentation | Project manager | Milestone | [15 empty] | M
Site launch | Project manager | Milestone | [29 empty] | M
Content
Lofthus introduction | Content creator | 50 |  | 4
Lofthus image | Content creator | 200 |  | 4 | 8
Product introduction | Content creator | 180 |  |  |  | 8 | 6
Footer information | Content creator | 20 |  |  |  |  | 2
Social media | Content creator | 40 | [6 empty] | 4
Product text | Content creator | 200 | [6 empty] | 4 | 8
Product image | Content creator | 50 | [8 empty] | 4
Product image large | Content creator | 50 | [8 empty] | 4
Article text | Content creator | 150 | [9 empty] | 8 | 8
Article images | Content creator | 80 | [11 empty] | 8
Article images large | Content creator | 80 | [12 empty] | 8
Call center info | Content creator | 40 | [13 empty] | 4
Email | Content creator | 40 | [13 empty] | 4
Submit confirmation | Content creator | 40 | [14 empty] | 4
Server
Buy Domain name | Web administrator | 50 | [6 empty] | 8
Set up servers | Web administrator | 200 | [7 empty] | 8 | 8 | 8
Design
Create colour palette | Designer | 50 | [6 empty] | 4
Create background design | Designer | 100 | [7 empty] | 8
Create layout and wireframes | Designer | 150 | [8 empty] | 8 | 8
Header logo | Designer | 40 | [10 empty] | 4
Footer logo | Designer | 40 | [10 empty] | 4
Sitemap | Designer | 50 | [11 empty] | 4
Link to "about us" | Designer | 50 | [11 empty] | 4
Product list link button | Designer | 50 | [12 empty] | 4
Contact form | Designer | 100 | [13 empty] | 8
Contact form submit | Designer | 40 | [14 empty] | 4
Development
Create logo as link | Front-end developer | 40 | [16 empty] | 4
Build Navigation | Front-end developer | 100 | [17 empty] | 8
Navigation location | Front-end developer | 50 | [18 empty] | 4
Order form product list | Front-end developer | 200 | [18 empty] | 4 | 8 | 8
Order form quantity | Front-end developer | 100 | [21 empty] | 8
Customer data | Front-end developer | 250 | [22 empty] | 8 | 8 | 8
Automatic call | Front-end developer | 30 | [25 empty] | 2
Clickable email link | Front-end developer | 100 | [26 empty] | 8
Contact for user info | Front-end developer | 150 | [27 empty] | 8 | 6
Resource hours - estimated |  |  | 40 | 16 | 16 | 16 | 12 | 40 | 20 | 24 | 24 | 24 | 16 | 16 | 12 | 16 | 8 | 40 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 8 | 8 | 6 | 40
Total hours | [31 empty] | 472

## Task list
Tasklist from the user stories
Each task listed in this document is based on a user story from the user story list of ‘must have’ for the website. The tasks has an assignee which is responsible for the execution of the task. An estimate with both story points and time is also added to each task.
Theme - Design
Epic - Style and design
Feature1 - Colours
Task title: Create colour palette
Task 1 - Assignee = Designer
Estimate - 50 points , 4 hours
Description: Create a palette of colours that can be used on the Website that match ‘Lofthus’ company, this will be presented at the customer presentation meeting and will be set as completed if accepted.
Task title: Create background design
Task 2 - Assignee = Designer
Estimate - 100 points - 8 hours
Description: Based on the colour palette from Task 1, set up suggested colours and images for the background of the site pages. This will be presented at the customer presentation meeting and will be set as completed if accepted.
Feature2 - Design
Task title: Create layout and wireframes
Task 1 - Assignee = Designer
Estimate 150 points . 16 hours
Description: Create a ‘default layout’ design for the website and set up wireframes for each of the sites pages, both for desktop and mobile.
Epic - Logo, header and nav
Feature 1 - Logos
Task title: header logo
Assignee - Designer
Estimate 40 points - 4 hours
Description: Gather the Logo assets from Lofthus and adjust these to fit on the website, use the design and wireframes to define which adjustments must be done to make the logo fit the page.
Task title: Create logo as a link
Assignee - Front-end developer
Estimate: 40 points - 4 hours
Description: Add the logo to each web page based on the wireframes and add a href that links to the front page. There is no need for the link on the actual front page html file.
Task title: Footer logo
Assignee - Designer
Estimate 40 points - 4 hours
Description: Add a Lofthus logo to the footer in the design and wireframe, make sure these logos are adjusted to fit the footer before coding begins.
Feature 2 - Navigation
Task title: Build navigation
Assignee - Front-end developer
Estimate 100 points - 8 hours
Description: Create a navigation in the header of each webpage, these must have the same style on all pages on the website.
Task title: Navigation ‘location’
Assignee - Front-end developer
Estimate 50 points - 4 hours
Description: Style the navigation so that the current page is highlighted in the navigation bar in the header of the page.
Feature 3 - Footer
Task title: Footer info
Assignee - Content creator
Estimate 20 points - 2 hours
Description: Gather the contact information of Lofthus that should be written and added to the footer of the website.
Task title: Site map
Assignee - Designer
Estimate 50 points - 4 hours
Description: create a design for the site map which will be included in the footer of the website. This will be added as navigation by a front-end developer.
Task title: social media
Assignee - content creator
Estimate 40 points - 4 hours
Description: Gather and adjust logos for Twitter, Facebook and Instagram , so these will match and be added to the footer of the website.
Theme - Main page
Epic 1 - Main page
Feature 1 - Lofthus Introduction
Task title - Lofthus introduction
Assignee - Content creator
Estimate 50 points - 4 hours
Description: Create an introduction text for the main page, it must describe what lofthus is producing and who they are in short.
Task title - Link to about us.
Assignee - Designer
Estimate 50 points - 4 hours
Description: Design a ‘about us’ button which can be used as a button in the Lofthus introduction.
Task title - Lofthus image
Assignee - Content creator
Estimate 100 points - 12 hours
Description: Take a trip to Lofthus and take some pictures. These must be of the facilities, the Lufths employees and their products. Prepare some images for the web pages based on the photos.
4
Feature 2 - Products
Task title - Product introduction
Assignee - Content creator
Estimate 150 points - 14 hours
Description: Create an article with pictures about the products of Lofthus. This will be added to the main page by a front-end-developer when finished.
Task title - Product list link button
Assignee - Designer
Estimate 50 points - 4 hours
Description: Design a button for ‘Product list’, this will be added to the product article on the main page by a Front-end developer when finished.
Theme - Order page
Epic 1 - Products and orders
Feature 1 - Product information
Task title - Product text
Assignee - Content creator
Estimate 200 points - 12 hours
Description: Gather information about the products of Lofthus and create a longer article than the one for the main page. This must be sectioned for each product.
Task title - product image
Assignee - Content creator
Estimate 50 points - 4 hours
Description - prepare an image for each product based on the assets gathered from Lofthus or the photos taken when visited lofthus in the ‘visit lofthus’ task. This will be added to each section in the product list on the order page by a front-end developer.
Task title - product image large
Assignee - Content creator
Estimate 40 points - 4 hours
Description - Prepare a larger version of the images from the previous task. These images will be added to the order page by a front-end developer when ready.
Feature 2 - Order form
Task title - Order form product list
Assignee - Front-end developer
Estimate 240 points - 24 hours
Description - Create an order form for the order page, this will include all the products in the Lofthus range. A customer must be able to see the product in a list with an image and short text.
Task title - Order form quantity
Assignee - Front-end developer
Estimate 100 points - 8 hours
Description - The order form must have a quantity field which will report how much of each product the customer wants.
Task title - Customer data
Assignee - Front-End developer
Estimate 250 points - 24 hours
Description - Add customer information fields to the order form, This must include customer name, last name, phone number, address and email.
Theme - ‘About us’ page
Epic 1 - lofthus information
Feature 1 - Lofthus article
Task title - Article text
Assignee - Content creator
Estimate - 150 points 16 hours
Description: Create a long article about lofthus and their products. This is the main article for the about us page which describes Lofthus, their production and heritage.
Task title - Article images
Assignee - Content creator
Estimate 80 points - 8 hours
Description: Create some images for the about us page based on the photos taken at Lofthus. These will be added with the article on the about us page.
Task title - image enlarge
Assignee - Content creator
Estimate 80 points - 8 hours
Description - Prepare larger images of the ones created in the ‘article images’ task. These will be the enlarged pictures displayed to the users visiting the page and clicking on the image to see the enlarged version. A front-end developer will add these to the about us page when ready.
Epic 2 - Contact lofthus
Feature 1 - customer call center
Task title - Call center info
Assignee - Content creator
Estimate 40 - 4 hours
Description: Create an overview of the contact information for Lofthus. This will be added to the ‘about us’ page for customers who want to contact Lofthus.
Task title - Automatic call
Assignee - Front-end developer
Estimate 30 points - 2 hours
Description: Add the info from the “call center” task to the ‘about us’ page and set the phone number as “call-able”.
Feature 2 - Email contact
Task title - Email
Assignee - Content creator
Estimate 40 points - 4 hours
Description: Find the contact email for lofthus and create a ‘email contact’ section for the “about us” page. This will be added to the page by a front-end developer.
Task title - Clickable email link
Assignee - Front-End Developer
Estimate 100 points - 8 hours
Description: Add the email section to the “about us” page and make the email link click-able so the email program on the users device will open and start an email to Lofthus.
Feature 3 - contact form
Task title - contact form
Assignee - Designer
Estimate 100 point - 8 hours
Description: Create a design for a contact form, how it should look and which colours to use. This will be implemented to the page by a front-end developer.
Task title - contact for user info
Assignee - Front-end developer
Estimate 150 points - 14 hours
Description: Create a contact form with the design from the result of the “contact form” task. The fields that must be added are; First name, Last name, Email, Address, Phone number.
Task title - Contact form submit
Assignee - Designer
Estimate 40 points - 4 hours
Description: Create a “submit” button for the contact form. This will be added to the contact form by a front-end developer.
Task title - Submit confirmation
Assignee - Content creator
Estimate 40 points - 4 hours
Description: Create a text which confirms that the contact form has been sent in, this will be added to the “about us” page by a front-end developer when finished. This will become visible after the user has clicked “Submit”.